## Funded
2026/27 ADP Deliverable Number | Deliverable Title (area of focus for this deliverable) [free text] | 2026/27 Deliverable Summary Brief summary of the deliverable, outlining the intended action and what this will achieve in 2026/27. [free text] | Deliverable funding position [Drop-Down] | Directorate / Business Area [Drop-Down] | Directorate Workstream / Programme [Optional] [free text] | Deliverable Lead [For Internal Use Only / not published in Cttee / Board paper] | SG Service Renewal Framework Principle [Drop-Down] | PSD Scotland Priority [Drop-Down] | Medium Term Priority [pre-defined list or free text] | Strategic Theme [Drop-Down] | Strategic Theme Detail [Drop-Down] | Primary strategic contribution [Drop-Down] | [Optional] Secondary strategic contribution [Drop-Down] | Strategic KPI Reference [pre-defined list or free text] | Intended impact of work What difference will this work make? e.g. to the h&sc workforce / patients / service users / Scottish citizens? | Q1 Milestones What you intend to have achieved by Q1 [free text] | Q2 Milestones What you intend to have achieved by Q2 [free text] | Q3 Milestones What you intend to have achieved by Q3 [free text] | Q4 Milestones What you intend to have achieved by Q4 [free text] | Indicative Milestones Year 2 - 2027/28 (High Level Summary) [free text] | Indicative Milestones Year 3 - 2028/29 (High Level Summary) [free text] | Risks to delivery [narrative highlighting any risks associated with this deliverable that are not already included in directorate risk registers] [free text]
FCGLS-2627-002 | Payroll Services 2026/27 | Embed unified Operating Model for payroll service delivery for 9 Boards. ( 90k staff pays per month) - Refining ways of working -Continuous improvement -Alignment and supporting Business Systems Programme for 2028 implementation. | Yes | FCGLS |  | John Connelly4@nhs.scot | People | Provide national shared service and infrastructure | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Service Excellence |  |  |  | - Implementation of Public Services Delivery Scotland payroll activities for the new organisation, ensuring staff are paid on time and accurately. -Preparing for implementation of GENU (Payroll Upgrade) and preparation for implementation eRostering and interface with Payroll. | - Implementation of the Alternative ServiceNow solution and implementation of relevant workflows, engagement with stakeholders. -Preparing and being involved in the Business Services Transformation Programme (Payroll System) including payroll SME and support for the procurement of the new system. | -Continue implementation of eRostering across 9 Boards. -Complete Roll out of Alternative ServiceNow solution. -Being involved in the Business Services Transformation Programme. | - Scope and define requirements for implementation of business systems across 9 boards. -Agree implementation plan and secure resources for implementation Q1-2028 |  |  | -There is a risk that PSD is unable to deliver timely and effective payroll services for health boards and staff, leading to payment delays, financial concerns and impacting PSD credibility for delivering a payroll shared service. -Continual increase demand on BAU across 9 boards around workforce change and new services potential being included in remit of PSD. -Staff capacity and resilience to maintain the delivery of weekly and monthly payments to 90k staff using legacy technologies, until BSP-Payroll fully implemented. -Ability to maintain BAU and release the required resources for implementation of BSP-Payroll.
FCGLS-2627-003 | Fraud Prevention | Deliver the CFS annual delivery plan to achieve the fiscal impact on fraud of £5.2m that will contribute to the three year target of £15.6m. This will be a combination of initiatives and activities resulting from fraud prevention, fraud detection and fraud recovered. This service is delivered to 21 Health Boards and the Independent Living Fund Scotland. | Yes | FCGLS |  | Gordon.Young2@nhs.scot | Population | Enable at scale improvement, innovation and implementation | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Financial Sustainability |  |  |  | Savings of £1.3m from fraud prevented or fraud recovered. Due to the nature of CFS work these savings can’t be guaranteed or measured each quarter, however, the annual saving target of £5.2million can be achieved. | Savings of £2.6m from fraud prevented or fraud recovered. Due to the nature of CFS work these savings can’t be guaranteed or measured each quarter, however, the annual saving target of £5.2million can be achieved. | Savings of £3.9m from fraud prevented or fraud recovered. Due to the nature of CFS work these savings can’t be guaranteed or measured each quarter, however, the annual saving target of £5.2million can be achieved. | Savings of £5.2m from fraud prevented or fraud recovered. |  |  | Recoveries of £5.2m not met, the impact of not achieving the reduction in fraud means that there will be less money to distribute to health boards to spend on frontline patient care. Reputational - Failure to deliver the forecasted savings would have a negative impact on CFS's reputation meaning Boards might be less inclined to work with us.
FCGLS-2627-006 | Counter Fraud Services - Patient Claims Team | The service operates across all 14 territorial Health Boards and is delivered by a specialist team of 9 staff, who collectively undertake approximately 80,000 checks each year to verify patient entitlement to exemptions from dental and ophthalmic charges. Thereby contributing to the delivery of the CFS ADP achieving a combined fiscal impact of £5.2million through targeted fraud prevention and detection activity. | Yes | FCGLS |  | Gordon.Young2@nhs.scot | Population | Provide national shared service and infrastructure | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Financial Sustainability | Service Excellence |  |  | Combined savings (fraud prevented and fraud recovered) of £1.3m from PCT, Detection, Fraud Control and Investigation Teams prevented or fraud recovered. Due to the nature of CFS work these savings can’t be guaranteed or measured each quarter, however, the annual saving target of £5.2million can be achieved. | Combined savings (fraud prevented and fraud recovered) of £2.6m from PCT, Detection, Fraud Control and Investigation Teams prevented or fraud recovered. Due to the nature of CFS work these savings can’t be guaranteed or measured each quarter, however, the annual saving target of £5.2million can be achieved. | Combined savings (fraud prevented and fraud recovered) of £3.9m from PCT, Detection, Fraud Control and Investigation Teams prevented or fraud recovered. Due to the nature of CFS work these savings can’t be guaranteed or measured each quarter, however, the annual saving target of £5.2million can be achieved. | Savings of £5.2m from fraud prevented or fraud recovered. |  |  | Recoveries of £5.2m not met, the impact of not achieving the reduction in fraud means that there will be less money to distribute to health boards to spend on frontline patient care. Reputational - Failure to deliver the forecasted savings would have a negative impact on CFS's reputation meaning Boards might be less inclined to work with us.
FCGLS-2627-007 | Counter Fraud Services - Detection Team | This service is delivered across all 21 Health Boards and the Independent Living Fund Scotland (ILFS) by a multidisciplinary team of 13 staff, comprising five intelligence staff, two criminal intelligence analysts, four statistical analysts, one financial investigator, and the National Counter Fraud Manager. The team processes and develops approximately 560 fraud referrals each year, with their combined activity contributing to the delivery of the CFS ADP and achieving a total fiscal impact of £5.2 million through targeted fraud prevention and detection activity. | Yes | FCGLS |  | Gordon.Young2@nhs.scot | Population | Provide national shared service and infrastructure | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Financial Sustainability | Service Excellence |  |  | Combined savings (fraud prevented and fraud recovered) of £1.3m from PCT, Detection, Fraud Control and Investigation Teams prevented or fraud recovered. Due to the nature of CFS work these savings can’t be guaranteed or measured each quarter, however, the annual saving target of £5.2million can be achieved. | Combined savings (fraud prevented and fraud recovered) of £2.6m from PCT, Detection, Fraud Control and Investigation Teams prevented or fraud recovered. Due to the nature of CFS work these savings can’t be guaranteed or measured each quarter, however, the annual saving target of £5.2million can be achieved. | Combined savings (fraud prevented and fraud recovered) of £3.9m from PCT, Detection, Fraud Control and Investigation Teams prevented or fraud recovered. Due to the nature of CFS work these savings can’t be guaranteed or measured each quarter, however, the annual saving target of £5.2million can be achieved. | Savings of £5.2m from fraud prevented or fraud recovered. |  |  | Recoveries of £5.2m not met, the impact of not achieving the reduction in fraud means that there will be less money to distribute to health boards to spend on frontline patient care. Reputational - Failure to deliver the forecasted savings would have a negative impact on CFS's reputation meaning Boards might be less inclined to work with us.
FCGLS-2627-007 | Counter Fraud Services - Fraud Control Team | This service is delivered across all 21 Health Boards and the Independent Living Fund Scotland (ILFS) by a team of 6 staff. The team undertakes fraud risk assessments, develops and delivers training materials, leads deterrence and disruption activity, and provides support to Health Boards in meeting the requirements of the Counter Fraud Standard. Through this activity, the service contributes directly to the delivery of the CFS ADP, achieving a combined fiscal impact of £5.2 million through targeted fraud prevention and detection activity. | Yes | FCGLS |  | Gordon.Young2@nhs.s | Population | Provide national shared service and infrastructure | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Financial Sustainability | Service Excellence |  |  | Combined savings (fraud prevented and fraud recovered) of £1.3m from PCT, Detection, Fraud Control and Investigation Teams prevented or fraud recovered. Due to the nature of CFS work these savings can’t be guaranteed or measured each quarter, however, the annual saving target of £5.2million can be achieved. | Combined savings (fraud prevented and fraud recovered) of £2.6m from PCT, Detection, Fraud Control and Investigation Teams prevented or fraud recovered. Due to the nature of CFS work these savings can’t be guaranteed or measured each quarter, however, the annual saving target of £5.2million can be achieved. | Combined savings (fraud prevented and fraud recovered) of £3.9m from PCT, Detection, Fraud Control and Investigation Teams prevented or fraud recovered. Due to the nature of CFS work these savings can’t be guaranteed or measured each quarter, however, the annual saving target of £5.2million can be achieved. | Savings of £5.2m from fraud prevented or fraud recovered. |  |  | Recoveries of £5.2m not met, the impact of not achieving the reduction in fraud means that there will be less money to distribute to health boards to spend on frontline patient care. Reputational - Failure to deliver the forecasted savings would have a negative impact on CFS's reputation meaning Boards might be less inclined to work with us.
FCGLS-2627-007 | Counter Fraud Services - Investigation Team | This service is delivered across all 21 Health Boards and the Independent Living Fund Scotland (ILFS) by a team of 11 staff who undertake criminal investigations into fraud and related offences. The team is responsible for reporting cases to the Crown Office and Procurator Fiscal Service, as well as to Health Boards, in line with agreed governance and evidential standards. Through this activity, the service contributes directly to the delivery of the CFS ADP, achieving a combined fiscal impact of £5.2 million through targeted fraud prevention and detection activity. | Yes | FCGLS |  | Gordon.Young2@nhs.scot | Population | Provide national shared service and infrastructure | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Financial Sustainability | Service Excellence |  |  | Combined savings (fraud prevented and fraud recovered) of £1.3m from PCT, Detection, Fraud Control and Investigation Teams prevented or fraud recovered. Due to the nature of CFS work these savings can’t be guaranteed or measured each quarter, however, the annual saving target of £5.2million can be achieved. | Combined savings (fraud prevented and fraud recovered) of £2.6m from PCT, Detection, Fraud Control and Investigation Teams prevented or fraud recovered. Due to the nature of CFS work these savings can’t be guaranteed or measured each quarter, however, the annual saving target of £5.2million can be achieved. | Combined savings (fraud prevented and fraud recovered) of £3.9m from PCT, Detection, Fraud Control and Investigation Teams prevented or fraud recovered. Due to the nature of CFS work these savings can’t be guaranteed or measured each quarter, however, the annual saving target of £5.2million can be achieved. | Savings of £5.2m from fraud prevented or fraud recovered. |  |  | Recoveries of £5.2m not met, the impact of not achieving the reduction in fraud means that there will be less money to distribute to health boards to spend on frontline patient care. Reputational - Failure to deliver the forecasted savings would have a negative impact on CFS's reputation meaning Boards might be less inclined to work with us.
FCGLS-2627-015 | Financial Operations: Contractor Finance - Primary care Practitioner payments | Deliver accurate and on time payments of c £3.3 bilion per annuml to primary care practitioner on behalf of Scottish Government and territorial health boards | Yes | FCGLS |  | Brian.McCabe2@nhs.scot | Population | Provide national shared service and infrastructure | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Service Excellence | Service Excellence |  |  | On time and accurate payments to each constituent. | On time and accurate payments to each constituent. | On time and accurate payments to each constituent. | On time and accurate payments to each constituent. |  |  | Risk of not achieving on time and accurate payments.
FCGLS-2627-016 | Financial Operations: Contractor Finance - Primary care Practitioner payments - payment verification | Carry out payment verification procedures on c£3.3m pa of to primary care practitioner on behalf of Scottish Government and territorial health boards to assist with the reduction of fraud in Primary Care. | Yes | FCGLS |  | Brian.McCabe2@nhs.scot | Population | Provide national shared service and infrastructure | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Service Excellence | Service Excellence |  |  | Carry out PV internal control procedures as agreed with Territorial Boards within signed Partnership Agreements and with engagement with Counter Fraud Services as necessary. | Carry out PV internal control procedures as agreed with Territorial Boards within signed Partnership Agreements and with engagement with Counter Fraud Services as necessary. | Carry out PV internal control procedures as agreed with Territorial Boards within signed Partnership Agreements and with engagement with Counter Fraud Services as necessary. | Carry out PV internal control procedures as agreed with Territorial Boards within signed Partnership Agreements and with engagement with Counter Fraud Services as necessary. |  |  | Risk of not fullfilling requirements under agreed Partnership Agreements.
FCGLS-2627-017 | Financial Operations: Contractor Finance - Scottish Infected Blood Support Scheme | Management of the Scottish Infected Blood Support Scheme (SIBSS) on behalf of the Scottish and UK Governments. This includes circa £15m of "regular" compensation payments and one off compensation amounts approved in line with the Scheme guidelines (eg c£40m in 2025/26). | Yes | FCGLS |  | Brian.McCabe2@nhs.scot | Population | Enable at scale improvement, innovation and implementation | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Service Excellence | Service Excellence |  |  | Efficient and timely processing of payments, applications and queries in relation to the Scheme. | Efficient and timely processing of payments, applications and queries in relation to the Scheme. | Efficient and timely processing of payments, applications and queries in relation to the Scheme. | Efficient and timely processing of payments, applications and queries in relation to the Scheme. |  |  | Risk of delayed payment to beneficiaries, risk of fraud related to the high value of amounts involved.Risk of delayed payment to beneficiaries, risk of fraud related to the high value of amounts involved.
FCGLS-2627-018 | Financial Operations: Contractor Finance - Clinical Negligence and Other Risks Indemnity Scheme (CNORIS) | Preparation of the CNORIS Annual report and supplementary reports for Scottish Government. | Yes | FCGLS |  |  | Population | Enable at scale improvement, innovation and implementation | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Service Excellence | Service Excellence |  |  | Provision of supplementary CNORIS reports to SG. | Provision of supplementary CNORIS reports to SG. | Approval of the CNORIS Annual report and supplementary reports for Scottish Government. | Provision of supplementary CNORIS reports to SG.
FIN 2026/27 1 | Procurement | Improved and optimised procurement to ensure we receive goods and services at the best price, quality and on time, and deliver savings target of 3.25% on addressable spend (average £22mn per annum). | PSD Scotland Funded (Baseline) | Finance | Finance & Procurement | Kenny McLean | N/A | N/A | Internal efficiency, sustainability & affordability | Performance | Maximise NES’s efficiency and demonstrate best value | Achieve best value in the delivery of our long term plan (transforming our business systems / governance / operating model) | N/A | SKPI36 - Projected variance of budgeting within 0.5% at year end | The Procurement savings directly impacts our financial health, and supports reinvestment in growth and innovation. Ensuring goods and services are obtained at the best price and quality also fosters stronger supplier relationships and enhances overall operational performance. | N/A - reports in Q4 only. | N/A - reports in Q4 only. | N/A - reports in Q4 only. | Deliver savings of 3.25% on addressable spend. | To be added | To be added | To be added
NP-2627-002 | National Procurement Commercial Workplan Savings | National Procurement’s goal for the FY2026-27 contract Workplan is to secure £10m savings. We will achieve this by developing and communicating a resourced workplan for Green RAG status projects, and execute the plan from 1 April 2026 to 21 March 2027. Secured savings will be reported quarterly against the plan. Heads of Strategic Sourcing will monitor and report monthly via the NP Governance Meeting kpis, sitreps and quarterly to the NHSS's Corporate Finance Network. This supports NHS Scotland financial sustainability. | Yes | NP |  | melinda.keir@nhs.scot; kris.lindsay@nhs.scot; simon.mollart@nhs.scot | Population | Enable at scale improvement, innovation and implementation | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Financial Sustainability |  |  |  | Workplan defined. Savings report issued. | Savings report issued | Savings report issued | Savings report issued |  |  | The workplan covers over 150 individual projects, if there is an overall identified risk in completion of the workplan such as staff availability or changes to the request on staff then this will be captured through the normal risk and issues log and governance meeting that occurs monthly
NP-2627-003 | National Distribution Service: Efficiency Improvement Programme | By end March 2027, optimise the NDS product portfolio , increasing cost-effectiveness of identified products by at least 10% as measured by efficiency gains and value benefit delivery. This will be achieved by developing a strategic options proposal aligned with the NP commercial workplan, NHSS financial sustainability goals and the NDS warehouse end-of-lease timetable (2031) for in scope products. | Yes | NP |  | melinda.keir@nhs.scot; iain.main@nhs.scot | Population | Enable at scale improvement, innovation and implementation | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Financial Sustainability |  |  |  | Conduct a comprehensive review of the current NDS product portfolio to identify cost drivers, inefficiencies, and areas for value enhancement. Engage stakeholders from NDS vendor base, health boards, NPW, CITF and NDS warehouse teams. Map the portfolio review findings to ensure strategic coherence. | Develop a detailed proposal with multiple strategic options for optimising the product portfolio, including cost-benefit analysis and projected efficiency gains. Present the strategic options to key stakeholders for feedback and secure approval for the selected optimisation pathway. Include a full-scope opportunity assessment profile and identifying options for 'quick-wins'. | Prepare a detailed implementation plan, including timelines, responsibilities, and resource requirements for the approval of all relevant stakeholders. Commence execution of the optimisation plan, closely monitoring progress against efficiency and value delivery targets. | Conduct a formal review of progress towards the 10% cost-effectiveness target, adjusting as necessary. At end of year assess overall outcomes, document efficiency gains and value delivered, and report results to stakeholders. |  |  | There is a risk of commercial pressure being present in workplan outcomes and therefore affecting the opportunities to deliver benefit. There is a risk of Implementation timescales being prohibitive depending on structure of workplan output and challenges around product change due to lead-time and/or stock holding levels. There is a risk that full stakeholder engagement is not achieved through challenges around resources and priority objectives.
NP-2627-004 | Business Services Programme - Procurement National Functional Lead | By 31 March 2027, provide national leadership as Procurement Functional Lead for the NHS Scotland Business Services Programme, ensuring delivery of agreed procurement outcomes for the 2026/27 programme year | Yes | NP |  | melinda.keir@nhs.scot; lynne.mccarthy@nhs.scot | People | Lead digital and data transformation | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Service Excellence | Financial Sustainability | ADP achievement | Support deliver of the NHSS Business Services Transformation Programme | ITSIT Evaluation complete Data Migration Strategy Published | Functional Negotiations Complete COM - Create Implementation Roadmap | Contract Awarded FBC Approved COM Agreed | Commence Delivery - Design, Configure, Build, Implementation |  |  | There is a risk that delivery of the system‑supported COM and procurement implementation plan is delayed due to governance approval dependencies and the complexity of multi‑Health Board readiness, impacting alignment with the Business Services Programme schedule.
NP-2627-005 | Health board Procurement Team workplan savings delivery | By the end of Q4 FY2026–27, deliver £250,000 in cost savings through CRES and cost avoidances | Yes | NP |  | melinda.keir@nhs.scot; Kate.henderson@nhs.scot | Population | Enable at scale improvement, innovation and implementation | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Financial Sustainability | Service Excellence | ADP achievement | Delivery of savings through procurement supports our financial position and enables reinvestment in other services across PSD Scotland | N/A - reports in Q4 only. | N/A - reports in Q4 only. | N/A - reports in Q4 only. | Deliver £250,000 of savings and cost avoidances |  |  | There is a risk that commercial instability, driven by current global conflicts, leads to greater than expected cost pressures
NP-2627-006 | NHSScotland Business Services Transformation 2026/27 local implementation | Support implementation of Business Services Transformation (expert input, requirements definition, influencing design of new service). Final Business Case | PSD Scotland Funded (Baseline) | Finance | Finance | Andrew.McLean3@nhs.scot; Brian.McCabe2@nhs.scot laura.howard3@nhs.scot | [8 empty] | Ensuring PSD Scotland fulfils its strategic and national objectives and demonstrates value for money. | Delivery against the overall Programme Plan | Delivery against the overall Programme Plan | Delivery against the overall Programme Plan | Delivery against the overall Programme Plan | Delivery against the overall Programme Plan | Delivery against the overall Programme Plan | There is a risk of possible resource constraint due to the implementation of competing projects. BST Programme implementation and delivery timescales might be impacted
NP-2627-007 | Finance - Governance and Control | Ensure annual accounts and supplementary returns for 2025/26 are signed and delivered to deadline and in line with Scottish Government reporting requirements as stated within the Scottish Public Finance Manual and NHS Annual Report and Accounts Manual.Delivery of effective financial governance, control transaction and treasury services across PSD Scotland covering a gross annual revenue budget of c£2.2 billion, £6 billion of payments made on behalf of NHS Scotland, supporting 7,000 trainees and over 6,000 employees, ensuring compliance with Standing Financial Instructions and the wider control framework. | PSD Scotland Funded (Baseline) | Finance | Finance | Andrew.McLean3@nhs.scot; Brian.McCabe2@nhs.scot laura.howard3@nhs.scot | [8 empty] | Open and transparent reporting of legacy organisations and PSD Scotland on the 2025/26 end of year and the 2026/27 financial position to ensure public confidence regarding how the organisations use / spends public money. | 1. The NES and NSS Annual Report and Accounts for 2025/26 approved by the Board and submitted to Scottish Government by 30th June 2026. 2.Completion of monthly balance sheet reconciliations. 3. Process of invoices in an timely basis. 4. Compliance with Board and Committee reporting requirements. 5. Statutory returns and payments (VAT, PAYE, SPPA) completed to deadlines | 1.Completion of monthly balance sheet reconciliations. 2. Process of invoices in an timely basis. 3. Compliance with Board and Committee reporting requirements. 4. Statutory returns and payments (VAT, PAYE, SPPA) completed to deadlines | 1. Audit Planning phase completed with Audit Scotland for the PSD Scotland Annual Report and Accounts 2026/27 2.Completion of monthly balance sheet reconciliations. 3. Process of invoices in an timely basis. 4. Compliance with Board and Committee reporting requirements." 5. Statutory returns and payments (VAT, PAYE, SPPA) completed to deadlines | 1,Deliver 2026/27 Annual Accounts timetable by end of Feb 2027 and Interim testing completed by Audit Scotland by March 27. 2. Completion of monthly balance sheet reconciliations. 3. Process of invoices in an timely basis. 4. Compliance with Board and Committee reporting requirements." 5. Statutory returns and payments (VAT, PAYE, SPPA) completed to deadlines | 1,Delivery, audit and approval of PSD Scotland Annual Report and Accounts 2. Completion of monthly balance sheet reconciliations. 3. Process of invoices in an timely basis. 4. Compliance with Board and Committee reporting requirements." 5. Statutory returns and payments (VAT, PAYE, SPPA) completed to deadlines | 1,Delivery, audit and approval of PSD Scotland Annual Report and Accounts 2. Completion of monthly balance sheet reconciliations. 3. Process of invoices in an timely basis. 4. Compliance with Board and Committee reporting requirements." 5. Statutory returns and payments (VAT, PAYE, SPPA) completed to deadlines | There is a risk that the Annual Report and Accounts and financial transactions are not compliant with Statutory requirements, the Standing Financial Instructions and the wider control framework.
NP-2627-008 | Finance - Finance Business Partnering | Develop a robust, balanced three year financial plan for 2026/27 (value c£2.2bn per annum) as part of the Medium Term Operational Plan. Working closely with Planning and directorates to ensure budgets are realistic, required savings are identified and activities demonstrate value for money. This enables the organisation to fulfil its strategic and national objectives within agreed funding envelopes. Monitoring of budgets across financial year with monthly updates to ET and SG (via FPR) and quarterly updates to Board. | PSD Scotland Funded (Baseline) | Finance | Finance | Andrew.McLean3@nhs.scot; Brian.McCabe2@nhs.scot laura.howard3@nhs.scot | [8 empty] | Ensuring PSD Scotland fulfils its strategic and national objectives and demonstrates value for money. | Financial reporting deadlines met. 2026/27 Directorate Budgets, approved by Board & SG, loaded to Efin and communicated to budget holders. | Financial reporting deadlines met. Work with Planning to develop and distribute guidance for Op planning process to all Directorates. | Financial reporting deadlines met. All Op plan meetings held and Directorate plans reviewed and consolidated and compared to anticipated SG funding. | Financial reporting deadlines met. Draft 3 year Financial Plan approved by Board and meet SG submission deadlines by the end of Q4. | Financial reporting deadlines met. Delivery of 3 year financial plan | Financial reporting deadlines met. Delivery of 3 year financial plan | There is a risk that we do not have the capacity to deliver BAU and increasing demand, in a period of significant change including the introduction of PSD Scotland and implementation of new Business Systems. With the formation of PSD Scotland there is a risk that significant efficiency targets will be set by SG that we are unable to deliver in the short to medium term.
NP-2627-009 | Financial Sustainability Action Plan 2026/27 | Continue to drive Financial Sustainability, creating an action plan for PSD Scotland to enhance Financial Management culture and manage financial resources effectively. • Achieve statutory financial targets in immediate/longer term • Improved accuracy of forecasts and initial project costs • Longer term horizon scanning reflected in plans • Increased understanding of cost drivers and service costs | PSD Scotland Funded (Baseline) | Finance | Finance | Andrew.McLean3@nhs.scot; Brian.McCabe2@nhs.scot laura.howard3@nhs.scot | [8 empty] | Ensuring PSD Scotland fulfils its strategic and national objectives and demonstrates value for money. | Financial balance | Financial balance | Financial balance | Financial balance | Financial balance | Financial balance | There is a risk that PSD Scotland is unable to deliver its statutory obligation to deliver services within approved funding limits, whilst delivering cash releasing efficiency savings targets (Capacity and Buy-In from Services -e.g. service costing project).
NP-2627-010 | Public Services Delivery Scotland (Finance) | Support and enable the work required for the implementation of Public Services Delivery Scotland (Finance) | PSD Scotland Funded (Baseline) | Finance | Finance | Andrew.McLean3@nhs.scot; Brian.McCabe2@nhs.scot laura.howard3@nhs.scot | [8 empty] | Ensuring PSD Scotland fulfils its strategic and national objectives and demonstrates value for money. | Phase 2 – Enhanced Operational State – Consolidate & Design (2026/27) | Phase 2 – Enhanced Operational State – Consolidate & Design (2026/27) | Phase 2 – Enhanced Operational State – Consolidate & Design (2026/27) | Phase 2 – Enhanced Operational State – Consolidate & Design (2026/27) | Provide expert financial advice for the delivery of the PSD Scotland strategic objectives | Provide expert financial advice for the delivery of the PSD Scotland strategic objectives | There is a risk that implementation of the PSD Scotland might be delayed due to lack of capacity, lack of mandate of decision and decision making with an overall agreed Framework.

## Subject to Funding
2026/27 ADP Deliverable Number | Deliverable Title (area of focus for this deliverable) [free text] | 2026/27 Deliverable Summary Brief summary of the deliverable, outlining the intended action and what this will achieve in 2026/27. [free text] | Deliverable funding position [Drop-Down] | Directorate / Business Area [Drop-Down] | Directorate Workstream / Programme [Optional] [free text] | Deliverable Lead [For Internal Use Only / not published in Cttee / Board paper] | SG Service Renewal Framework Principle [Drop-Down] | PSD Scotland Priority [Drop-Down] | Medium Term Priority [pre-defined list or free text] | Strategic Theme [Drop-Down] | Strategic Theme Detail [Drop-Down] | Primary strategic contribution [Drop-Down] | [Optional] Secondary strategic contribution [Drop-Down] | Strategic KPI Reference [pre-defined list or free text] | Intended impact of work What difference will this work make? e.g. to the h&sc workforce / patients / service users / Scottish citizens? | Q1 Milestones What you intend to have achieved by Q1 [free text] | Q2 Milestones What you intend to have achieved by Q2 [free text] | Q3 Milestones What you intend to have achieved by Q3 [free text] | Q4 Milestones What you intend to have achieved by Q4 [free text] | Indicative Milestones Year 2 - 2027/28 (High Level Summary) [free text] | Indicative Milestones Year 3 - 2028/29 (High Level Summary) [free text] | Risks to delivery [narrative highlighting any risks associated with this deliverable that are not already included in directorate risk registers] [free text]
Assure-2627-009 | Estates Rationalisation | 1)Delivery of Strategic Assessment for Warehouses and Gyle 2)Disposal of Anderson House as per Property Transaction Handbook (PTH) | No | NHSScotland Assure |  | Melinda.Keir@nhs.scot; Barrie.Richardson@nhs.scot | People | Enable at scale improvement, innovation and implementation | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Financial Sustainability |  |  |  | 1) Statement of Requirement established, option appraisal complete and Strategic Assessment Programmes meeting timescales. 2) Anderson House Clearance complete and landlord disposal negotiations complete with settlement figure agreed. | 1) Strategic Assessment 1st Draft ready for internal board approval. 2) Anderson House successfully surrendered and PTH followed. | 1) Strategic Assessment issued to SG for 1st round of feedback. Changes made where required by PSD Scotland. 2) Anderson House Dilapidation Settlement figure paid. | 1) Strategic Assessment Submitted to SG for Warehousing and Gyle. |  |  | 1) PSD Scotland governance for decisions incurs additional time to programme. 2) There is a risk that the landlord Dilapidation Settlement figure for the disposal of Anderson House is higher than expected.
Assure-2627-010 | PSD Future Warehouse Model – Lease transition & logistics resilience | To scope and design a future warehouse model that supports the continuity of logistics services for NHS Scotland, including feasibility of establishing a new facility, managing transition from the current warehouse as the lease concludes, and ensuring alignment with long-term operational and strategic objectives. | No | NHSScotland Assure |  | melinda.keir@nhs.scot; david.mackay8@nhs.scot | Community | Provide national shared service and infrastructure | Future NDS provision model and warehouse continuity (2031 lease horizon) | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Service Excellence | Financial Sustainability | Business case approved; preferred warehouse model selected; transition plan agreed; service continuity maintained (no critical supply interruptions). | Ensure continuity and resilience of national logistics services for NHS Scotland, reducing operational risk from lease expiry and enabling a modernised, sustainable warehouse operation (including potential automation and systems integration). Supports reliable supply and improved service performance for Boards and patients. | Initiate project and governance; confirm lease/estate constraints; complete stakeholder map and engagement plan; document current-state warehouse operations and requirements. | Complete demand/capacity baseline and resilience assessment; develop longlist of options (new facility / partnership / upgrade); begin estates/site feasibility and high-level costs; assess medicines-in-scope implications. | Shortlist and evaluate options (cost/benefit, sustainability, automation, service continuity); draft preferred option; develop transition approach and outline business case; complete initial risk assessment and mitigation plan. | Finalise business case and implementation roadmap agree preferred option and decision point define procurement/estates route, timeline and resource plan; produce detailed transition plan and benefits/KPIs. |  |  | Risk of service disruption during transition; dependencies on lease expiry/landlord commitments; insufficient stakeholder engagement; resourcing constraints; uncertainty in funding approvals and estates availability.
FCGLS-2627-020 | Financial Operations: Provision of Financial Governance and transactional support to other Territorial Boards | The delivery of Financial services including accounts payable and receivable transaction services, treasury functions, finanical controls, technical accounting and regulatory compliance support and assistance with the preparation of their Annual Report and Accounts on a shared service basis to other NHS boards including Public Health Scotland (PHS), Heath Improvement Scotland (HIS), NHS24 and The State Hospital covering additional annual revenue budgets of c£250m. | No | FCGLS |  | Brian.McCabe2@nhs.scot | Population | Provide national shared service and infrastructure | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Service Excellence | Service Excellence |  |  | Provision of services in line with provisions of underlying SLAs. | Provision of services in line with provisions of underlying SLAs. | Provision of services in line with provisions of underlying SLAs. | Provision of services in line with provisions of underlying SLAs.

## Deliverables Removed (hidden)
2026/27 ADP Deliverable Number | Deliverable Title (area of focus for this deliverable) [free text] | 2026/27 Deliverable Summary Brief summary of the deliverable, outlining the intended action and what this will achieve in 2026/27. [free text] | Deliverable funding position [Drop-Down] | Directorate / Business Area [Drop-Down] | Directorate Workstream / Programme [Optional] [free text] | Deliverable Lead [For Internal Use Only / not published in Cttee / Board paper] | SG Service Renewal Framework Principle [Drop-Down] | PSD Scotland Priority [Drop-Down] | Medium Term Priority [pre-defined list or free text] | Strategic Theme [Drop-Down] | Strategic Theme Detail [Drop-Down] | Primary strategic contribution [Drop-Down] | [Optional] Secondary strategic contribution [Drop-Down] | Strategic KPI Reference [pre-defined list or free text] | Intended impact of work What difference will this work make? e.g. to the h&sc workforce / patients / service users / Scottish citizens? | Q1 Milestones What you intend to have achieved by Q1 [free text] | Q2 Milestones What you intend to have achieved by Q2 [free text] | Q3 Milestones What you intend to have achieved by Q3 [free text] | Q4 Milestones What you intend to have achieved by Q4 [free text] | Indicative Milestones Year 2 - 2027/28 (High Level Summary) [free text] | Indicative Milestones Year 3 - 2028/29 (High Level Summary) [free text] | Risks to delivery [narrative highlighting any risks associated with this deliverable that are not already included in directorate risk registers] [free text]
FCGLS-2627-005 | NHSScotland Business Services Transformation 2026/27 local implementation | Support implementation of Business Services Transformation (expert input, requirements definition, influencing design of new service). Final Business Case | Yes | FCGLS |  | Andrew.McLean3@nhs.scot; Brian.McCabe2@nhs.scot | People | Provide national shared service and infrastructure | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Service Excellence |  |  |  | Delivery against the overall Programme Plan | Delivery against the overall Programme Plan | Delivery against the overall Programme Plan | Delivery against the overall Programme Plan |  |  | There is a risk of possible resource constraint due to the implementation of competing projects. BST Programme implementation and delivery timescales might be impacted
FIN 2026/27 2 | Finance - Governance Operations | Ensure annual accounts and supplementary returns for 2025/26 are signed and delivered to deadline and in line with Scottish Government reporting requirements as stated within the Scottish Public Finance Manual and NHS Annual Report and Accounts Manual. | PSD Scotland Funded (Baseline) | Finance | Finance & Procurement | Monica Halcro | N/A | N/A | Internal efficiency, sustainability & affordability | Performance | Maximise NES’s efficiency and demonstrate best value | Achieve best value in the delivery of our long term plan (transforming our business systems / governance / operating model) | N/A | SKPI36 - Projected variance of budgeting within 0.5% at year end | Open and transparent reporting of NES's end of year financial and performance position to ensure public confidence regarding how NES uses / spends public money. | Annual Report and Accounts for 2025/26 approved by the Board and submitted to Scottish Government by 30th June 2026. | N/A | Audit Planning phase completed with Audit Scotland for the Annual Report and Accounts 2025/26 | Deliver 2024/25 Annual Accounts timetable by end of Feb 2024. Interim testing completed by Audit Scotland by March 25. | To be added | To be added | To be added
FIN 2026/27 3 | Finance - Finance Business Partnering | Develop a robust, balanced three year financial plan for 2026/27 (value c£815m per annum) as part of the Medium Term Operational Plan. Working closely with NES Planning and NES directorates to ensure budgets are realistic, required savings are identified and activities demonstrate value for money. This enables the organisation to fulfil its strategic and national objectives within agreed funding envelopes. Monitoring of budgets across financial year with monthly updates to ET and SG (via FPR) and quarterly updates to Board. | PSD Scotland Funded (Baseline) | Finance | Finance & Procurement | Alan Young | N/A | N/A | Internal efficiency, sustainability & affordability | Performance | Maximise NES’s efficiency and demonstrate best value | Achieve best value in the delivery of our long term plan (transforming our business systems / governance / operating model) | N/A | SKPI36 - Projected variance of budgeting within 0.5% at year end | Ensuring NES fulfils its strategic and national objectives and demonstrating value for money. | Financial reporting deadlines met. 2025/26 Directorate Budgets, approved by Board & SG, loaded to Efin and communicated to budget holders. | Financial reporting deadlines met. Work with Planning to develop and distribute guidance for Op planning process to all Directorates. | Financial reporting deadlines met. All Op plan meetings held and Directorate plans reviewed and consolidated and compared to anticipated SG funding. | Financial reporting deadlines met. Draft 3 year Financial Plan approved by Board and meet SG submission deadlines by the end of Q4. | To be added | To be added | To be added
FCGLS-2627-001 | Financial Sustainability Action Plan 2026/27 | Continue to drive the implementation of the NSS Financial Sustainability Action Plan to enhance Financial Management culture in NSS and manage NSS financial resources effectively. • Achieve statutory financial targets in immediate/longer term • Improved accuracy of forecasts and initial project costs • Longer term horizon scanning reflected in plans • Increased understanding of cost drivers and service costs | Yes | FCGLS |  | Andrew.McLean3@nhs.scot | Population | Enable at scale improvement, innovation and implementation | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Financial Sustainability |  |  |  | Financial balance | Financial balance | Financial balance | Financial balance |  |  | There is a risk that NSS is unable to deliver its statutory obligation to deliver services within approved funding limits, whilst delivering cash releasing efficiency savings targets (Capacity and Buy-In from Services -e.g. service costing project).
FCGLS-2627-010 | Business Finance - Management Accounting | Provision of Management Accounting Services to Budget Holders within PSD Scotand and Public Health Scotland (as per SLA agreement) Over 250 delegated budget holders across PSD and PHS Total Budget is £582k (Establishment 12wte). Funding is mostly Baseline £501k. Sub Teams are split by Pillar of Activity: Pay - supporting all workforce analysis, and providing an interface between HR, Payroll and Service Managers, to ensure workforce financial information is accurately managed and consistently reported Non-pay – managing all non-pay expenditure, including pass-through expenditure and contract support, providing a key interface between procurement, NP colleagues, operational finance colleagues supporting accounts payable and VAT and technical accounting advice, to ensure consistency, challenge, contract compliance and value for money from our non-pay spend. Income – driving a consistent approach to the management of income recovery, SLA management, by applying consistent cost recovery principles across all areas of our business. | Yes | FCGLS |  | Andrew.McLean3@nhs.scot | Population | Enable at scale improvement, innovation and implementation | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Financial Sustainability | Service Excellence |  |  | Financial reporting deadlines met. 2025/26 Directorate Budgets, approved by Board & SG, loaded to Efin and communicated to budget holders. | Financial reporting deadlines met. On-going, action focussed support to Budget Holders (Data Driven approach to focus on key opportunities, risks and issues) | Financial reporting deadlines met. On-going, action focussed support to Budget Holders (Data Driven approach to focus on key opportunities, risks and issues) | Financial reporting deadlines met. On-going, action focussed support to Budget Holders (Data Driven approach to focus on key opportunities, risks and issues) |  |  | 'Roles & Responsibilities' unclear between Finance and Delegated Budget Holders. Capacity to deliver BAU and increasing demand, in a period of significant change including the introduction of PSD Scotland and implementation of new Business Systems.
FCGLS-2627-004 | Public Services Delivery Scotland (Finance) | Support and enable the work required for the implementation of Public Services Delivery Scotland (Finance) | Yes | FCGLS |  | Andrew.McLean3@nhs.scot; Brian.McCabe2@nhs.scot | People | Enable at scale improvement, innovation and implementation | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Service Excellence |  |  |  | Phase 2 – Enhanced Operational State – Consolidate & Design (2026/27) | Phase 2 – Enhanced Operational State – Consolidate & Design (2026/27) | Phase 2 – Enhanced Operational State – Consolidate & Design (2026/27) | Phase 2 – Enhanced Operational State – Consolidate & Design (2026/27) |  |  | There is a risk that implementation of the PSD Scotland might be delayed due to lack of capacity, lack of mandate of decision and decision making with an overall agreed Framework.
FCGLS-2627-011 | Business Finance - Business Control | The Business Control service provided expert financial support and advice to the "Key Decision Makers" (over 50 of the c250 delegated budget holders deemed to be KDMs) within each Directorate across PSD Scotland and PHS under the agreed SLA. Each Directorate has a named, dedicated Business Controller to own key business relationships with senior managers and budget holders, managing financial planning, performance management and reporting, providing insight and reviewing and challenging decision making This service also include a Corporate Planning & Reporting role and PMO function to support and co-ordinated the delivery of both internal and external reporting into SG Finance Total Budget is £939k Establishment 10.8wte). Funding is mostly baseline (£875k) | Yes | FCGLS |  | Andrew.McLean3@nhs.scot | Population | Enable at scale improvement, innovation and implementation | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Financial Sustainability | Service Excellence |  |  | Financial reporting deadlines met. 2025/26 Directorate Budgets, approved by Board & SG, loaded to Efin and communicated to budget holders. | Financial reporting deadlines met. On-going, action focussed support to Budget Holders (Data Driven approach to focus on key opportunities, risks and issues). Drive Integrated Planning requirements and arrangements, working closely with Coporate colleagues to ensure expected outcomes. | Financial reporting deadlines met. On-going, action focussed support to Budget Holders (Data Driven approach to focus on key opportunities, risks and issues). Financial Analysis of Directorate Integrated Service Plans to present to and inform discussions at Budget Summit (and PHS equivalent) | Financial reporting deadlines met. On-going, action focussed support to Budget Holders (Data Driven approach to focus on key opportunities, risks and issues). Draft Financial Plan approved by Board and meet SG submission deadlines by the end of Q4. |  |  | 'Roles & Responsibilities' unclear between Finance and Delegated Budget Holders. Capacity to deliver BAU and increasing demand, in a period of significant change including the introduction of PSD Scotland and implementation of new Business Systems.
FCGLS-2627-012 | Business Finance - Business Intelligence & Analytics (BI&A) | The BI&A service (part of the wider Business Control sub-team) provides a service which places data at the heart of finance and provides consistent, accurate information to influence and support decision making across the organisation. BI&A maintain and improve the Finance Dashboard which is a resource which all delegated Budget Holders (including PHS) use to access their monthly financial results and forecasts to inform decision making. BI&A also produce the visualisations and certain insights to Directorate SLT Finance Reports on a monthly basis (again covering PHS also) Total Budget is £217k (Establishment 3wte) mostly funded by Baseline | Yes | FCGLS |  | Andrew.McLean3@nhs.scot | Population | Enable at scale improvement, innovation and implementation | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Financial Sustainability | Service Excellence |  |  | Publish new detailed Budgets for FY26/27 on Finance Dashboard for all delegated Budget Holders to access. | Maintain and improve reporting tools. Provide insights and analysis to support decision making by business. Support production of Coporate and Directorate reports. | Maintain and improve reporting tools. Provide insights and analysis to support decision making by business. Support production of Coporate and Directorate reports. | Maintain and improve reporting tools. Provide insights and analysis to support decision making by business. Support production of Coporate and Directorate reports. |  |  | 'Roles & Responsibilities' unclear between Finance and Delegated Budget Holders. Capacity to deliver BAU and increasing demand, in a period of significant change including the introduction of PSD Scotland and implementation of new Business Systems. Too much time on reporting, reducing opportunities and benefits from more analysis (across various data sets).
FCGLS-2627-013 | Business Finance - Finance Business Partnering | The Business Partners will work strategically across the organisation, focussing on driving value from key strategic themes and services provided by PSD on behalf of NHS Scotland. They will measure the impact PSD makes on the wider health system from its activities and strategic developments. The Business Partners will not be involved in the routine financial management planning, performance and reporting cycle, but will be future focused. They will have a key role in horizon scanning and in supporting service developments, improvements and transformation within PSD and wider NHS Scotland. Total Budget is £491k (Establishment 5wte). Funding is mostly baseline (£378k). | Yes | FCGLS |  | Andrew.McLean3@nhs.scot | Population | Enable at scale improvement, innovation and implementation | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Financial Sustainability | Service Excellence |  |  | Ongoing support to key PSD & NHSS projects and programmes. | Ongoing support to key PSD & NHSS projects and programmes. | Ongoing support to key PSD & NHSS projects and programmes. | Ongoing support to key PSD & NHSS projects and programmes. |  |  | 'Roles & Responsibilities' unclear between Finance and Delegated Budget Holders. Capacity to deliver BAU and increasing demand, in a period of significant change including the introduction of PSD Scotland and implementation of new Business Systems. Income Targets within Budget related to project and programme activity - most is secure but some arises / confirmed in year.
FCGLS-2627-014 | Business Finance - Project Accounting (Finance) | The Projects team provide support to various programmes – supporting business case development, options appraisal, and support for the financial management of change programmes, including benefits realisation and measurement of value delivered. | Yes | FCGLS |  | Andrew.McLean3@nhs.scot | Population | Enable at scale improvement, innovation and implementation | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Financial Sustainability | Service Excellence |  |  | Ongoing support to key PSD & NHSS projects and programmes. | Ongoing support to key PSD & NHSS projects and programmes. | Ongoing support to key PSD & NHSS projects and programmes. | Ongoing support to key PSD & NHSS projects and programmes. |  |  | 'Roles & Responsibilities' unclear between Finance and Delegated Budget Holders. Capacity to deliver BAU and increasing demand, in a period of significant change including the introduction of PSD Scotland and implementation of new Business Systems. Income Targets within Budget related to project and programme activity - most is secure but some arises / confirmed in year.
FCGLS-2627-019 | Financial Operations: Provisions of Financial governance and transactional support to PSD Scotland | Delivery of effective financial governance, control transaction and treasury services across PSD Scotland covering a gross annual revenue budget of c£1.1 billion, net assets of c£200m and over 3,500 employees, ensuring compliance with Standing Financial Instructions and the wider control framework and the provision of technical financial accounting and VAT services. | Yes | FCGLS |  | Brian.McCabe2@nhs.scot | Population | Enable at scale improvement, innovation and implementation | Financial Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Service Excellence | Service Excellence |  |  | 1.Completion of monthly balance sheet reconciliations. 2. Process of invoices in an timely basis. 3. Compliance with Board and Committee reporting requirements. | 1.Completion of monthly balance sheet reconciliations. 2. Process of invoices in an timely basis. 3. Compliance with Board and Committee reporting requirements. | 1.Completion of monthly balance sheet reconciliations. 2. Process of invoices in an timely basis. 3. Compliance with Board and Committee reporting requirements. | 1.Completion of monthly balance sheet reconciliations. 2. Process of invoices in an timely basis. 3. Compliance with Board and Committee reporting requirements. |  |  | Non compliance with Standing Financial Instructions and the wider control framework.