## Funded
2026/27 ADP Deliverable Number | Deliverable Title (area of focus for this deliverable) [free text] | 2026/27 Deliverable Summary Brief summary of the deliverable, outlining the intended action and what this will achieve in 2026/27. [free text] | Deliverable funding position [Drop-Down] | Directorate / Business Area [Drop-Down] | Directorate Workstream / Programme [Optional] [free text] | Deliverable Lead [For Internal Use Only / not published in Cttee / Board paper] | SG Service Renewal Framework Principle [Drop-Down] | PSD Scotland Priority [Drop-Down] | Medium Term Priority [pre-defined list or free text] | Strategic Theme [Drop-Down] | Strategic Theme Detail [Drop-Down] | Primary strategic contribution [Drop-Down] | [Optional] Secondary strategic contribution [Drop-Down] | Strategic KPI Reference [pre-defined list or free text] | Intended impact of work What difference will this work make? e.g. to the h&sc workforce / patients / service users / Scottish citizens? | Q1 Milestones What you intend to have achieved by Q1 [free text] | Q2 Milestones What you intend to have achieved by Q2 [free text] | Q3 Milestones What you intend to have achieved by Q3 [free text] | Q4 Milestones What you intend to have achieved by Q4 [free text] | Indicative Milestones Year 2 - 2027/28 (High Level Summary) [free text] | Indicative Milestones Year 3 - 2028/29 (High Level Summary) [free text] | Risks to delivery [narrative highlighting any risks associated with this deliverable that are not already included in directorate risk registers] [free text]
DEN 2026/27 11 | Oral Health Improvement Programmes - delivery of existing courses and training with concurrent review & redesign. | Deliver oral health improvement training through blended learning programmes (archetype 4). Provide a range of development sessions based upon prioritised health board needs to support oral health improvement programmes and reduce health inequalities. The oral health improvement programmes will include archetype 1 to 4 resources from Open Badges to learning programmes for use as continuous learning and development for health and social care staff. | PSD Scotland Funded (Baseline) | Dental | Dental Workforce Development | Thomas Lamont | People | Drive workforce planning, education and development | Education, training & workforce development | People | Lead and deliver education, training and CPD across health & social care workforce | Support transformation in roles and ways of working across h&sc | Encourage positive behaviours and workplace practices so staff across the h&sc workforce experience a culture aligned to [NHS Scotland] values | SKPI12 - % of learners indicating they are 'satisfied' or 'very satisfied' with their learning experience | Health & Social Care and priority patient groups. Training the h&sc workforce to deliver National Oral Health Improvement Programmes. | Deliver the oral health improvement blended learning course, and development sessions based upon priorities and health board needs. | Deliver the oral health improvement blended learning course, and development sessions based upon priorities and health board needs. | Deliver the oral health improvement blended learning course, and development sessions based upon priorities and health board needs. | Deliver the oral health improvement blended learning course, and development sessions based upon priorities and health board needs. | As per previous year | As per previous year | Uptake on programmes - workplace restrictions. New programme delivery challenges.
PPT 2026/27 9 | Co-ordination of support to trainers delivering Beyond Bystander training and anti-racism training in health and social care organisations. | Support the roll-out of train the trainer approaches in health and social care organisations by providing training and ongoing peer support, evaluation and best practice approaches to inclusive workplace practices, tackling discrmination and harassment , reducing health inequalities and supporting person-centred care | PSD Scotland Funded (Baseline) | Planning, Performance & Transformation | Equality, Diversity and Human Rights | Katy Hetherington | People | Drive workforce planning, education and development | Education, training & workforce development | Partnerships | Provide equality & human rights education | Encourage positive behaviours and workplace practices so staff across the h&sc workforce experience a culture aligned to [NHS Scotland] values | Support 'Once for Scotland' principles by sharing resources / learning / experience with partners to maximise value and impact | SKPI10 - Number of health and social care staff accessing NES learning products as a % of the health and social care workforce | Health and social care organisations are equipped to deliver training to staff which will support a workfoce that is equipped to address discrmination and harassment in the workplace and to reduce inequalities. | Community of practice established to support trainers. | Community of practice supported for trainers and gaps in skills identified. | Identify any further capability building training that is required to support the models | Community of practice meeting regularly and support needs identified and met. | Cohort of trainers skilled to deliver Beyond Bystander and anti-racism training across health and social care organisations. | Interventions to support the behaviours and culture in health and social care to for equality, diversity and inclusion and to prevent discrimination and harassment. | N/A
SCC 2026/27 5 | Health Inequalities | Advance NES's approach to Health Equity and to addressing Health Inequalities as part of the organisational contribution to the Population Health framework: raise awareness within NES of the impact of health inequalities and embed a health inequalities approach in our education and training programmes. | PSD Scotland Funded (Baseline) | Social Care & Communities | Health Inequalities | Gordon Paterson | Population | Drive workforce planning, education and development | Education, training & workforce development | People | Support NES staff through new career pathways, wellbeing initiatives & professional development | Support transformation in roles and ways of working across h&sc | Support 'Once for Scotland' principles by sharing resources / learning / experience with partners to maximise value and impact | SKPI09 - Total number of accesses to NES learning products | Having a health inequalities sensitive NES workforce. Supporting the embedding of a health inequalities approach in learning resources for the health and social care workforce. | Scope and assess NHSD and wider HSC workforce needs | Collaborate with stakeholders to plan response to assessed needs | Deliver with partners the response plan | Continue to deliver / evaluate implementation | •Population health KSF/ learning resources as per priorities (including health inequalities) | •Contribute to learning on Population Health | N/A
| Anchors strategy and delivery for PSD Scotland | Develop and deliver the PSD Scotland approach to Anchors, including national leadership, partner engagement, action delivery and performance reporting to provide a clear strategic framework for contributing to community wealth building, wellbeing and employability outcomes. | PSD Scotland Funded (Baseline) | Planning, Performance & Transformation / Strategy, Performance & Service Transformation |  | Christina Bichan/Lee Neary | Population | Support system-reform and public service integration | Education, training & workforce development | People | Maximise efficiency and demonstrate best value | Contribute to community wealth building and improving population health through employability and skills | Widening access to careers in h&sc |  | Through national leadership and partner action on Anchors, PSD Scotland will strengthen its contribution to community wealth building, employability and wellbeing, helping translate organisational intent into measurable social and economic impact. | PSD Scotland Anchors approach, reporting, governance and priority actions for 2026/27 agreed, with links established to national partner groups and internal delivery leads. | Priority actions underway, including partner engagement, measures, parental employability and reporting arrangements to track progress against agreed Anchors commitments. 2024/25 and 2025/26 reporting to Scottish Government | Delivery and reporting are embedded across priority actions, with evidence of contribution to community wealth building, employability and wellbeing outcomes used to refine the approach. | Development of end-year progress report aligned with SG reporting requirements, with agreed priorities for the next phase of PSD Scotland Anchors delivery and alignment to wider organisational strategy and planning. | Expand and deepen delivery of the Anchors approach across PSD Scotland, with stronger measurement, partner collaboration and integration into business planning. | Embed PSD Scotland as a mature Anchor institution with sustained delivery, clearer outcome evidence and stronger contribution to national and local priorities. | Risks include dependency on partner alignment, limited baseline data, diffuse ownership across the organisation, capacity constraints and difficulty evidencing impact consistently across multiple workstreams.

## Subject to Funding
2026/27 ADP Deliverable Number | Deliverable Title (area of focus for this deliverable) [free text] | 2026/27 Deliverable Summary Brief summary of the deliverable, outlining the intended action and what this will achieve in 2026/27. [free text] | Deliverable funding position [Drop-Down] | Directorate / Business Area [Drop-Down] | Directorate Workstream / Programme [Optional] [free text] | Deliverable Lead [For Internal Use Only / not published in Cttee / Board paper] | SG Service Renewal Framework Principle [Drop-Down] | PSD Scotland Priority [Drop-Down] | Medium Term Priority [pre-defined list or free text] | Strategic Theme [Drop-Down] | Strategic Theme Detail [Drop-Down] | Primary strategic contribution [Drop-Down] | [Optional] Secondary strategic contribution [Drop-Down] | Strategic KPI Reference [pre-defined list or free text] | Intended impact of work What difference will this work make? e.g. to the h&sc workforce / patients / service users / Scottish citizens? | Q1 Milestones What you intend to have achieved by Q1 [free text] | Q2 Milestones What you intend to have achieved by Q2 [free text] | Q3 Milestones What you intend to have achieved by Q3 [free text] | Q4 Milestones What you intend to have achieved by Q4 [free text] | Indicative Milestones Year 2 - 2027/28 (High Level Summary) [free text] | Indicative Milestones Year 3 - 2028/29 (High Level Summary) [free text] | Risks to delivery [narrative highlighting any risks associated with this deliverable that are not already included in directorate risk registers] [free text]
NMAHP 2026/27 7 | Learning Disabilities education resources | Develop educational resources that support workforce to address health inequalities experienced by people with learning disabilities and which promote inclusion and wellbeing. Action -With partners design and test workforce education resources focused on a) creating capapble environments and b) understanding major health conditions, including application to people with complex needs. Implement recommendations of the evaluation of 'Essentials of LD' programme conducted in 2025/26. | Unconfirmed SG Funded | NMAHP | Mental Health and Wellbeing | Audrey Taylor | People | Drive workforce planning, education and development | Education, training & workforce development | Partnerships | Provide equality & human rights education | Support 'Once for Scotland' principles by sharing resources / learning / experience with partners to maximise value and impact | Support 'Once for Scotland' principles by sharing resources / learning / experience with partners to maximise value and impact | SKPI11 - % of learners that tell us their education & training will improve their practice | Workforce more able to take targeted action to address health inequalities experienced by people with learning disabilities, leading to improved outcomes for individuals, families, and carers. | Engage with partners to agree and plan two education sessions, including focus on health checks Review recommendations/findings of evaluation and develop implimentation plan | Deliver one education session/resource focused on capable environments and reasonable adjustments, | Co design and deliver one learning event focused on personhood and voice of people with complex needs, and their families and carers | Deliver one e-learning module focused on major health conditions in context of LD | Further collaboration with LD Drivers focused on reasonable adjustments Continued delivery of education focused on people with complex needs (include health checks) | Delivery of education resources for wider workforce to support mitigation of health inequalities experienced by people with Learning Disabilities | N/A
NMAHP 2026/27 49 | Continue to raise the profile and demonstrate the impact of AHPs reflecting the AHP Public Health implementation Plan and Scotland's Population Health Framework | Subject to funding we will raise the profile of the contribution of the AHP workforce within the Population Health Framework for Scotland objectives and the Scottish AHP Public Health strategic implementation plan 2022 to 2027 | Unconfirmed SG Funded | NMAHP | Public Health | Angela King | People | Drive workforce planning, education and development | Education, training & workforce development | People | Lead and deliver education, training and CPD across health & social care workforce | Understand and articulate national and local workforce needs to inform planning and service delivery | Support 'Once for Scotland' principles by sharing resources / learning / experience with partners to maximise value and impact | SKPI09 - Total number of accesses to NES learning products | Strengthened AHP workforce contribution to public health, reducing health inequalities through targeted workforce development and leadership. | Delivery of minimum of 2 webinars and 2 COP events in conjunction with Scottish Governments on the Population Health Framework | We will continue to support boards with the occupational classification index of AHP workforce data relating to Public Health. Undertake a mapping exercise of "Embedding Public Health into Clinical Services"(NHS England) comparing practice in Scotland | Delivery of a hybrid AHP in PH event demonstrating impact and linking to AHP day/centenary year. Evaluation of educational solutions for AHPs to demonstrate their impact in practice.Respond to commission of educational resources identified by stakeholders from the evaluation. | Report on the visibility and impact of this programme of work to raise the profile of the AHP contribution to the wider Public Health workforce and provision of recommendations | Dependent upon funding, respond to stakeholder commissions and national policy directives | Dependent upon funding, respond to stakeholder commissions and national policy directives | N/A

## Deliverables Removed (hidden)
2026/27 ADP Deliverable Number | Deliverable Title (area of focus for this deliverable) [free text] | 2026/27 Deliverable Summary Brief summary of the deliverable, outlining the intended action and what this will achieve in 2026/27. [free text] | Deliverable funding position [Drop-Down] | Directorate / Business Area [Drop-Down] | Directorate Workstream / Programme [Optional] [free text] | Deliverable Lead [For Internal Use Only / not published in Cttee / Board paper] | SG Service Renewal Framework Principle [Drop-Down] | PSD Scotland Priority [Drop-Down] | Medium Term Priority [pre-defined list or free text] | Strategic Theme [Drop-Down] | Strategic Theme Detail [Drop-Down] | Primary strategic contribution [Drop-Down] | [Optional] Secondary strategic contribution [Drop-Down] | Strategic KPI Reference [pre-defined list or free text] | Intended impact of work What difference will this work make? e.g. to the h&sc workforce / patients / service users / Scottish citizens? | Q1 Milestones What you intend to have achieved by Q1 [free text] | Q2 Milestones What you intend to have achieved by Q2 [free text] | Q3 Milestones What you intend to have achieved by Q3 [free text] | Q4 Milestones What you intend to have achieved by Q4 [free text] | Indicative Milestones Year 2 - 2027/28 (High Level Summary) [free text] | Indicative Milestones Year 3 - 2028/29 (High Level Summary) [free text] | Risks to delivery [narrative highlighting any risks associated with this deliverable that are not already included in directorate risk registers] [free text]
COR 2026/27 2 | Anchors Plan | Continue to advance our Anchors Strategic Plan (ASP) for 2026/27 through the achievement of SMART objectives that reflect both our national role supporting the Scottish Government Health and Social Care Anchors programme (strategic support and engagement in the Anchors Workforce Strategy Group and Place and Wellbeing Programme Board and data and dashboard support for national ASP metrics) and internal work in relation to TBC for 2026/27. | PSD Scotland Funded (Baseline) | Corporate | Planning. Performance and Transformation | Christina Bichan | Population | Drive workforce planning, education and development | Education, training & workforce development | People | Maximise NES’s efficiency and demonstrate best value | Contribute to community wealth building and improving population health through employability and skills | Widening access to careers in h&sc | SKPI17 - Total accesses of the NHS Scotland Careers website | By collaborating with our local and national partners we will use our expertise in the delivery of high-quality education and training, skills development and employability and the innovative use of technology to improve outcomes for local communities and the environment. | TBC - awaiting information / confirmation from Anchors Workforce Strategy Group in relation to 26/27 deliverables supporting the Understanding and Improving the NHS Anchors Application Experience’ in September 2024. NES Planning to review 26/27 deliverables for other directorates and identify other 26/27 milestones related to Anchors work. Update March 2026 - milestones to include reference to work support Scottish Government 'Earn as You Learn' recommendations following approval of funding to extend post supporting EaYL work within NES. | TBC - as per Cell R23 | TBC - as per Cell R23 | TBC - as per Cell R23 | TBC | TBC | N/A