## Funded
2026/27 ADP Deliverable Number | Deliverable Title (area of focus for this deliverable) [free text] | 2026/27 Deliverable Summary Brief summary of the deliverable, outlining the intended action and what this will achieve in 2026/27. [free text] | Deliverable funding position [Drop-Down] | Directorate / Business Area [Drop-Down] | Directorate Workstream / Programme [Optional] [free text] | Deliverable Lead [For Internal Use Only / not published in Cttee / Board paper] | SG Service Renewal Framework Principle [Drop-Down] | PSD Scotland Priority [Drop-Down] | Medium Term Priority [pre-defined list or free text] | Strategic Theme [Drop-Down] | Strategic Theme Detail [Drop-Down] | Primary strategic contribution [Drop-Down] | [Optional] Secondary strategic contribution [Drop-Down] | Strategic KPI Reference [pre-defined list or free text] | Intended impact of work What difference will this work make? e.g. to the h&sc workforce / patients / service users / Scottish citizens? | Q1 Milestones What you intend to have achieved by Q1 [free text] | Q2 Milestones What you intend to have achieved by Q2 [free text] | Q3 Milestones What you intend to have achieved by Q3 [free text] | Q4 Milestones What you intend to have achieved by Q4 [free text] | Indicative Milestones Year 2 - 2027/28 (High Level Summary) [free text] | Indicative Milestones Year 3 - 2028/29 (High Level Summary) [free text] | Risks to delivery [narrative highlighting any risks associated with this deliverable that are not already included in directorate risk registers] [free text]
Assure-2627-001 | NHS Scotland Climate Sustainability | Delivery of 90% of the thematic area activity blueprint deliverables attributable to NHSScotland Assure programmed within the financial year 2026/27 for the NHSScotland Climate Emergency and Sustainability Programme. | Yes | NHSScotland Assure |  | Melinda.Keir@nhs.scot; Stuart.Brown3@nhs.scot; lesley.walsh3@nhs.scot | Community | Enable at scale improvement, innovation and implementation | Clinate Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Climate Sustainability |  |  |  | Deliverables confirmed and agreed by the programme. Progress update on completed deliverables for Q1. | Progress update on cumulative completed deliverables for Q2. | Progress update on cumulative completed deliverables for Q3. | Total completed deliverables for 26/27. |  |  | There is a risk that delivery of the priority national workstreams for the Climate Change, Sustainability & Environment is negatively impacted due to gaps in staff levels.
Assure-2627-002 | Electricity carbon reduction | Reduce carbon emissions associated from electricity use by 10% decrease based on 2022/23 baseline. | Yes | NHSScotland Assure |  | Melinda.Keir@nhs.scot; kathryn.logan@nhs.scot; Robert.Seamark@nhs.scot | Community | Enable at scale improvement, innovation and implementation | Clinate Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Climate Sustainability |  |  |  | Installation of solar PV (photovoltaic panels) at Bogelshole Road. | Replacement of solar PV at Jack Copland Centre. | Review solar performance and grid usage. | Assessment of year against baseline year electricity carbon emissions. |  |  | Grid electricity demand increase due to estates utilisation increase.
Assure-2627-003 | Gas carbon reduction | Reduce carbon emissions associated from gas use by 20% decrease based on 2022/23 baseline. | Yes | NHSScotland Assure |  | Melinda.Keir@nhs.scot; kathryn.logan@nhs.scot; Robert.Seamark@nhs.scot | Community | Enable at scale improvement, innovation and implementation | Clinate Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Climate Sustainability |  |  |  | Installation of Automated Meter Readings at Gartnavel and Foresterhill. | Review and performance progress update | Review and performance progress update | Assessment of year with outcomes and lessons learned |  |  | Gas demand increase due to estates utilisation increase.
Assure-2627-004 | Water carbon reduction | Reduce carbon emissions associated from water use by 50% decrease based on 2022/23 baseline. | Yes | NHSScotland Assure |  | Melinda.Keir@nhs.scot; kathryn.logan@nhs.scot; Robert.Seamark@nhs.scot | Community | Enable at scale improvement, innovation and implementation | Clinate Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Climate Sustainability |  |  |  | Installation of Automatic Meter Readings at Gartnavel and Foresterhill. | Review and performance progress update. | Review and performance progress update. | Assessment of year with outcomes and lessons learned. |  |  | Water demand increase due to estates utilisation increase.
Assure-2627-005 | EV Charging Infrastructure | Provision of electric vehicle charging points across NSS at all key estates (where possible), enabling the transition to an electric fleet and meeting agreed charging-capacity targets. | Yes | NHSScotland Assure |  | Melinda.Keir@nhs.scot; kathryn.logan@nhs.scot; Robert.Seamark@nhs.scot | Community | Enable at scale improvement, innovation and implementation | Clinate Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Climate Sustainability |  |  |  | Installation of EV Charging infrastructure at Bogleshole Road and Foresterhill | Replacement of EV charging infrastructure at NDS Canderside. | Installation of High Voltage substation. to support EV charging infrastructure at Jack Copland Centre. | Installation of EV charging infrastructure at Jack Copland Centre |  |  | Loss of funding due to delivery of projects not meeting Scottish Government timeframes.
Assure-2627-006 | Waste reduction | Achievement of improved waste management performance, with residual waste to be reduced below 50% of the combined residual and recyclate waste stream based on 2022/23 baseline. | Yes | NHSScotland Assure |  | Melinda.Keir@nhs.scot; kathryn.logan@nhs.scot; Robert.Seamark@nhs.scot | Community | Enable at scale improvement, innovation and implementation | Clinate Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Climate Sustainability |  |  |  | Review waste performance for FY 2025/26 to identify high waste producing estates. | Waste audit programme commenced. | Review of waste audit output. | Assessment of year with outcomes and lessons learned. |  |  | Waste segregation performance does not improve, leading to poor recycling performance and increased residual waste tonnes.
Assure-2627-007 | Climate Change Risk Assessment review | Completion and publication of the Climate Change Risk Assessment (CCRA), incorporating the integrated flood risk assessment and thermal study. | Yes | NHSScotland Assure |  | Melinda.Keir@nhs.scot; kathryn.logan@nhs.scot; Robert.Seamark@nhs.scot | Community | Enable at scale improvement, innovation and implementation | Clinate Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Climate Sustainability |  |  |  | Review of flood risk assessment. | Review of thermal study. | Update and share Climate Change Risk Assessment for review prior publication. | Assessment of year with outcomes and lessons learned . |  |  | No risks or issues are identified within this ADP.
Assure-2627-008 | Estates Compliance Activities | Undertake AP roles for Water, Electrical, Ventilation, Lifts, Confined Spaces, Pressure Systems and Asbestos in accordance with guidance. Update SCART. Ensure Safety Groups take place. Ensure statutory engineering inspections are completed. Attendance at national groups, CDM compliance | Yes | NHSScotland Assure |  | barrie.richardson@nhs.scot | Community | Provide national shared service and infrastructure | Clinate Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Service Excellence | Financial Sustainability | No RIDDOR- 100% | Statutory compliance. | Safety Reports reviewed and quality checked through FM safety group and three directorate governance | Safety Reports reviewed and quality checked through FM safety group and three directorate governance | Safety Reports reviewed and quality checked through FM safety group and three directorate governance | Safety Reports reviewed and quality checked through FM safety group and three directorate governance |  |  | Risks and issues managed through the Safety Governance
FIN 2026/27 4 | Climate change and sustainability | Ongoing implementation of NES Climate Emergency & Sustainability Strategy (2024-27), including the continued development of consistent approach to climate change and sustainability awareness in NES education and training programmes. | PSD Scotland Funded (Baseline) | Finance | Finance & Procurement | Jim Boyle | Community | Drive workforce planning, education and development | Internal efficiency, sustainability & affordability | Performance | Maximise NES’s efficiency and demonstrate best value | Achieve best value in the delivery of our long term plan (transforming our business systems / governance / operating model) | N/A | SKPI34 - CO2 emissions (estates) | Supporting the wider NHS Scotland effort to address the climate emergency and helping to ensure the health and social care workforce are aware of / understand the climate emergency via the provision of education and training. | Supporting the implementation of the NES Climate Emergency and Sustainability (CE&S) Strategy (2024-27) via a range of activities including education and training delivery being taken forward via the NES CE&S Clinical Sub Group and ongoing improvements to climate-related target measurement and reporting. | Supporting the implementation of the NES Climate Emergency and Sustainability (CE&S) Strategy (2024-27) via a range of activities including education and training delivery being taken forward via the NES CE&S Clinical Sub Group and ongoing improvements to climate-related target measurement and reporting. | Supporting the implementation of the NES Climate Emergency and Sustainability (CE&S) Strategy (2024-27) via a range of activities including education and training delivery being taken forward via the NES CE&S Clinical Sub Group and ongoing improvements to climate-related target measurement and reporting. | Supporting the implementation of the NES Climate Emergency and Sustainability (CE&S) Strategy (2024-27) via a range of activities including education and training delivery being taken forward via the NES CE&S Clinical Sub Group and ongoing improvements to climate-related target measurement and reporting. | As per prior year | As per prior year | N/A
NP-2627-001 | Electricity Decarbonisation | To enable electricity decarbonisation through Power Purchasing Agreement (PPAs) have service agreements with all Health Boards and achieve final stage of contracting process for 10% of NHSS Electricity demand by end March 2027. | Yes | NP |  | melinda.keir@nhs.scot; stevie.mclaughlin@nhs.scot; peter.beukes@nhs.scot | Community | Enable at scale improvement, innovation and implementation | Clinate Sustainability | Underpin | Underpin - improvement priority, challenging us to continually improve the quality of the services we provide that are essential to the functioning of the wider health and care system | Climate Sustainability |  |  |  | Achieve final stage of contracting process for PPAs amounting to 2% of volume usage; Finalise full complement of category reports; Implement daily management processes and start maintaining category reports; Complete signing of MOU/SLA with 4 HBs. | Achieve final stage of contracting process for PPAs amounting to 4%of volume usage; Complete signing of MOU/SLA with 8 HBs; Launch and manage intern mentoring program for B5 and B7 roles. | Achieve final stage of contracting process for PPAs amounting to 8% of volume usage; Complete signing of MOU/SLA with 14 HBs; Monitor social value objectives in CBG program. | Achieve final stage of contracting process for PPAs amounting to 10% of volume usage; Complete signing of MOU/SLA with 22 HBs; Continue intern mentoring and report on job creation impact. |  |  | Risk of PPA negotiations extending beyond timeline; Workforce capacity disruption for programmes; Risk that HBs are not engaged or ready to procure renewable energy due to governance and decision-making structure not being in place.

## Subject to Funding
2026/27 ADP Deliverable Number | Deliverable Title (area of focus for this deliverable) [free text] | 2026/27 Deliverable Summary Brief summary of the deliverable, outlining the intended action and what this will achieve in 2026/27. [free text] | Deliverable funding position [Drop-Down] | Directorate / Business Area [Drop-Down] | Directorate Workstream / Programme [Optional] [free text] | Deliverable Lead [For Internal Use Only / not published in Cttee / Board paper] | SG Service Renewal Framework Principle [Drop-Down] | PSD Scotland Priority [Drop-Down] | Medium Term Priority [pre-defined list or free text] | Strategic Theme [Drop-Down] | Strategic Theme Detail [Drop-Down] | Primary strategic contribution [Drop-Down] | [Optional] Secondary strategic contribution [Drop-Down] | Strategic KPI Reference [pre-defined list or free text] | Intended impact of work What difference will this work make? e.g. to the h&sc workforce / patients / service users / Scottish citizens? | Q1 Milestones What you intend to have achieved by Q1 [free text] | Q2 Milestones What you intend to have achieved by Q2 [free text] | Q3 Milestones What you intend to have achieved by Q3 [free text] | Q4 Milestones What you intend to have achieved by Q4 [free text] | Indicative Milestones Year 2 - 2027/28 (High Level Summary) [free text] | Indicative Milestones Year 3 - 2028/29 (High Level Summary) [free text] | Risks to delivery [narrative highlighting any risks associated with this deliverable that are not already included in directorate risk registers] [free text]

## Deliverables Removed (hidden)
2026/27 ADP Deliverable Number | Deliverable Title (area of focus for this deliverable) [free text] | 2026/27 Deliverable Summary Brief summary of the deliverable, outlining the intended action and what this will achieve in 2026/27. [free text] | Deliverable funding position [Drop-Down] | Directorate / Business Area [Drop-Down] | Directorate Workstream / Programme [Optional] [free text] | Deliverable Lead [For Internal Use Only / not published in Cttee / Board paper] | SG Service Renewal Framework Principle [Drop-Down] | PSD Scotland Priority [Drop-Down] | Medium Term Priority [pre-defined list or free text] | Strategic Theme [Drop-Down] | Strategic Theme Detail [Drop-Down] | Primary strategic contribution [Drop-Down] | [Optional] Secondary strategic contribution [Drop-Down] | Strategic KPI Reference [pre-defined list or free text] | Intended impact of work What difference will this work make? e.g. to the h&sc workforce / patients / service users / Scottish citizens? | Q1 Milestones What you intend to have achieved by Q1 [free text] | Q2 Milestones What you intend to have achieved by Q2 [free text] | Q3 Milestones What you intend to have achieved by Q3 [free text] | Q4 Milestones What you intend to have achieved by Q4 [free text] | Indicative Milestones Year 2 - 2027/28 (High Level Summary) [free text] | Indicative Milestones Year 3 - 2028/29 (High Level Summary) [free text] | Risks to delivery [narrative highlighting any risks associated with this deliverable that are not already included in directorate risk registers] [free text]